## Sheet1
Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
Developer becomes unwell/ill | Project would be incomplete | Low | High | Developer/Divine Entity | Ask for an extension | Hand hygeine and avoid extreme sports
Failure to meet the MVP | Fail the project | Low | High | Developer | Weep | Plan the project thoroughly with prioritoisation of tasks and asking for help from trainers where required
Hardware failure | Lost work and inability to complete project | Low | High | Developer | Inform trainers of issues, source hardware from elsewhere | Ensure work regularly backed up to remote repo
Cannot find solution to problem | Time lost | High | Low | Developer | Help from trainers | Look through course content and notes, search for solutions online on StackOverflow
Unable to achieve sufficient test coverage | Lost marks | Medium | Medium | Developer | Help from trainers | Attend workshop on testing, research testing and look through course content
Tests fail | Methods/software not working as expected | Medium | Medium | Developer | Evaluate tests and methods to determine where it is failing and correct as required | Write method and test code carefully. Could implement test-driven development or test methods as created
Methods don't work as expected | Project would not function as required | Medium | High | Developer | Correct method and code | Test methods, check methods working as expected as methods created
Incorrect user input | API stop working due to exceptions | High | High | Developer | Refactor methods to throw exceptions | Develop code to expect exceptions as the project is built